## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Jansevakam : Web Framework for NGO Outreach |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A. P. Shah Institute of Technology, Information Technology
PROJECT GUIDE |  | Prof. Ganesh Gourshete |  |  |  |  | DATE | [6 empty] | 2022-03-08
WBS NUMBER | TASK TITLE | TNSK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Y, S. Su | 2021-07-10 | 2021-07-26 | 3 | 100% | bar: WEEK 1 M to WEEK 3 F
1.1.1 | Research paper finalization | Y, S. Su | 2021-07-10 | 2021-07-26 | 3 | 100% | bar: WEEK 2 M to WEEK 4 F; WEEK 5 R to WEEK 7 F
1.2 | Project Title | Y, S. Su | 2021-07-10 | 2021-07-26 | 1 | 100% | bar: WEEK 2 W to WEEK 3 W; WEEK 10 M
1.3 | Abstract | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Y, S. Su | 2018-03-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.7 | Scope | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 R to WEEK 3 F
1.8 | Technology stack | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 R to WEEK 3 F
1.9 | Benefits for environment | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 R to WEEK 3 F
1.1 | Benefits for society | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 R to WEEK 3 F
1.11 | Applications | Y, S. Su | 2021-08-23 | 2021-08-30 | 1 | 100% | bar: WEEK 3 R to WEEK 3 F
2 | Project Design |  |  |  |  | 100%
2.1 | Proposed System | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 2 M; WEEK 6 M to WEEK 6 F
2.4 | Class Diagram | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F; WEEK 12 F
2.5 | Use Case Diagram | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 6 M to WEEK 6 F
2.6 | Modules | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 11 M to WEEK 12 R
2.6.1 | User registration | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F; WEEK 11 M to WEEK 12 R
2.6.2 | Post creation and Interaction | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F; WEEK 11 M to WEEK 12 R
2.6.3 | Model for post recommendation | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F; WEEK 9 W to WEEK 9 F; WEEK 11 M to WEEK 12 R
2.6.4 | Profile page | Y, S. Su | 2021-09-19 | 2021-09-27 | 1 | 100% | bar: WEEK 5 M to WEEK 6 F; WEEK 9 W to WEEK 9 F; WEEK 12 F
3 | Project Implementation
3.1 | User registration | Y, S. Su | 2022-02-04 | 2022-02-10 | 2 | 100% | bar: WEEK 8 M to WEEK 9 F
3.2 | Post creation and Interaction | Y, S. Su | 2022-02-11 | 2022-02-17 | 2 | 100% | bar: WEEK 8 M to WEEK 9 F
3.3 | Model for post recommendation | Y, S. Su | 2022-02-18 | 2022-02-24 | 4 | 100% | bar: WEEK 6 M to WEEK 9 F
3.4 | Profile page | Y, S. Su | 2022-02-25 | 2022-03-02 | 3 | 100% | bar: WEEK 7 M to WEEK 9 F
3.4 | Making website design better | Y, S. Su | 2022-03-03 | 2022-03-09 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
4 | Testing
4.1 | Design of Test Cases | Y, S. Su | 2022-01-07 | 2022-01-24 | 3 | 100% | bar: WEEK 9 M to WEEK 11 F
4.2 | User registration Unit Testing | Y, S. Su | 2022-01-27 | 2022-02-03 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
4.3 | User authentication Unit Testing | Y, S. Su | 2022-02-04 | 2022-02-10 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
4.4 | Backend logic testing | Y, S. Su | 2022-02-11 | 2022-02-17 | 1 | 100%
4.5 | Flask Unit Testing | Y, S. Su | 2022-02-18 | 2022-02-24 | 1 | 100%
4.6 | Unit testing | Y, S. Su | 2022-02-25 | 2022-03-02 | 1 | 100%
4.7 | Model Training Unit Testing | Y, S. Su | 2022-03-03 | 2022-03-09 | 1 | 100%
4.8 | Modules Integration Testing | Y, S. Su | 2022-03-10 | 2022-03-16 | 2 | 100%
4 | Report Preparation
5.1 | BlackBook | Y, S. Su | 2022-01-07 | 2022-01-24 | 2 | 100% | bar: WEEK 10 F to WEEK 12 F
5.2 | PPT | Y, S. Su | 2022-01-27 | 2022-02-03 | 1 | 100% | bar: WEEK 10 F to WEEK 12 F
5.3 | Gantt Chart | Y, S. Su | 2022-02-04 | 2022-02-10 | 1 | 100% | bar: WEEK 10 F to WEEK 12 F